## Roadmap
SPIEDR - Remediation Roadmap
Client: SPIEDR Ltd. (www.spiedr.com) ¦ Owner: Francis Marc Uy (SEO) ¦ Account lead: Shawn Moore ¦ Created 17 Sep 2026 ¦ Horizon 18 Sep - 12 Nov 2026
Phase | Focus | Window | Effort (est.) | Owner | Exit criteria
Phase 0 | Baseline and approvals | 18-24 Sep 2026 | 3-5 h | Francis / Shawn | Crawl archived, baselines exported, edit path confirmed
Phase 1 | High-leverage internal links | 18 Sep - 1 Oct 2026 | 8-12 h | Francis / Dev | About 30 in-content links across 4 target pages; re-crawl confirms
Phase 2 | Reporting hygiene + second-tier pages | 2-15 Oct 2026 | 6-9 h | Francis | Refreshed keyword set live before 6 Oct report; template updated
Phase 3 | Blog architecture | 16 Oct - 12 Nov 2026 | 14-20 h | Francis / Dev / Content | Every post reachable in 2 clicks with at least one contextual inbound link
Parallel | Google Business Profile data gap | Week 1 onward | TBD | GBP access holder | Reviews and call-click tracking confirmed firing, or cause identified
Effort envelope: roughly 31-46 hours total across eight weeks, assuming our team ships the edits. If SPIEDR ships them, our side drops to roughly 18-25 hours and the schedule extends by their turnaround. Estimates based on page counts, not a fixed quote.
Targets in this workbook are directional. Rankings respond to competitor activity and Google algorithm changes outside our control - no specific position outcome is promised.

## Task Tracker
Task Tracker
Update the Status column as work ships. Filter by Phase, Owner or Priority using the header dropdowns.
ID | Phase | Task | Owner | Priority | Effort | Due | Depends on | Status | Notes
0.1 | Phase 0 | Post Slack thread reply on the September report | Francis | High | 0.5 h | 2026-09-19 | - | Not started | Draft ready at slack-thread-reply-draft.md - review before posting
0.2 | Phase 0 | Run Screaming Frog crawl of spiedr.com, archive to crawls/spiedr/ | Francis | High | 1 h | 2026-09-22 | - | Not started | Send a browser User-Agent - the site is behind Mod_Security and rejects default crawler headers
0.3 | Phase 0 | Export Semrush Position Tracking daily data 1-30 Sept as baseline | Francis | High | 0.5 h | 2026-10-01 | - | Not started | Campaign 2084675
0.4 | Phase 0 | Export GSC page-level performance for September | Francis | High | 0.5 h | 2026-10-01 | - | Not started | National, all devices
0.5 | Phase 0 | Confirm who ships on-page edits - SPIEDR team or ours | Shawn | Critical | 0.5 h | 2026-09-19 | - | Not started | BLOCKING for Phase 1
0.6 | Phase 0 | Confirm approval model - per page or batch | Shawn | High | 0.5 h | 2026-09-19 | - | Not started | Affects Phase 1 and Phase 3 turnaround
0.7 | Phase 0 | Confirm the WordPress theme can support hub templates | Dev | Medium | 1 h | 2026-09-24 | - | Not started | Prevents discovering a blocker in Week 5
1A | Phase 1 | Add 6 in-content links to /roof-sprinkler-system/ | Dev / Francis | Critical | 2-3 h | 2026-09-26 | 0.5 | Not started | Zero inbound links today. Six keywords, about 460/mo combined, all stuck between #12 and #21. See Link Build List tab
1B | Phase 1 | Add 13 product-page links to /mark-3-pump/ | Dev / Francis | Critical | 2-3 h | 2026-09-26 | 0.5 | Not started | Defends "portable fire pumps canada" - was #1 until 11 Sept, #16 by 16 Sept. Vary the anchors
1C | Phase 1 | Add 8-10 links to /fire-embers/ from the wildfire-prep cluster | Dev / Francis | High | 2-3 h | 2026-10-01 | 0.5 | Not started | Top organic traffic page on the site, currently zero inbound in-content links
1D | Phase 1 | Add 6 links to /spiedr-fire-pump-protection-systems/ | Content / Dev | High | 2-3 h | 2026-10-01 | 0.5 | Not started | Needs sentences written rather than words wrapped - no page uses the exact phrase unlinked
1E | Phase 1 | Re-crawl and verify inbound counts on all four target pages | Francis | High | 1 h | 2026-10-01 | 1A, 1B, 1C, 1D | Not started | Confirms the links rendered in content, not in a sidebar widget
2A | Phase 2 | Rebuild the Position Tracking keyword set | Francis | Critical | 2-3 h | 2026-10-03 | - | Not started | MUST land before the 6 Oct report is assembled or October repeats September false alarms
2B | Phase 2 | Switch report rank movement to a monthly or 7-day average | Francis / Shawn | High | 1-2 h | 2026-10-03 | - | Not started | Day-1-vs-day-31 comparison is what turned a two-day wobble into a reported -13
2C | Phase 2 | Add the Desktop/BC vs national note to the report template | Francis | Medium | 0.5 h | 2026-10-03 | - | Not started | Position Tracking and GSC will never agree - readers should know why
2D | Phase 2 | Second-tier link targets: /spiedr-sprinkler-trailers/, /spiedr-wildfire-sprinkler-kit/, /about-us/history/, /waterax-pumps/ | Dev / Francis | Medium | 3-4 h | 2026-10-15 | 1E | Not started | Lower volume than Phase 1 but still unsupported
3.1 | Phase 3 | Group the 93 posts into 3-4 topic hubs | Francis | High | 3-4 h | 2026-10-22 | - | Not started | Wildfire Preparedness / BC Fire Bans and Regulations / Equipment and Pumps / Wildfire Science
3.2 | Phase 3 | Build hub landing pages linking every post in their cluster | Dev / Content | High | 6-8 h | 2026-11-05 | 3.1, 0.7 | Not started | The structural fix for the 45 unlinked posts
3.3 | Phase 3 | Link the hubs from main nav or a resources block | Dev | High | 1-2 h | 2026-11-05 | 3.2 | Not started | Otherwise the hubs are orphaned themselves
3.4 | Phase 3 | Add related-reading blocks to the 20 highest-potential posts | Content | Medium | 4-6 h | 2026-11-12 | 3.1 | Not started | Three or four contextual links each
3.5 | Phase 3 | Refresh and prominently link the BC fire bans post | Content / Francis | High | Folded into 3.4 | 2026-11-12 | 3.1 | Not started | Ranks #25-31 across about 20 variants totalling 15,000+/mo. Regulations change annually so a freshness pass is needed. Highest ceiling on the account
G.1 | Parallel | Confirm the GBP listing is connected to the reporting integration | GBP access holder | High | 1 h | 2026-09-26 | - | Not started | 0 reviews / 0 rating / 0 call clicks against 1.32K impressions reads as a sync failure
G.2 | Parallel | Check call-click tracking is enabled on the listing | GBP access holder | High | 0.5 h | 2026-09-26 | G.1 | Not started | The gbp-audit MCP tool is hard-blocked at 0 req/min and needs a Cloud Console fix - use BrightLocal
G.3 | Parallel | If reviews genuinely are zero, raise a review generation programme | Shawn | Medium | - | 2026-10-06 | G.1 | Not started | Separate conversation with Bob and Natalie

## Link Build List
Phase 1 - Link Build List
Existing mentions = unlinked occurrences of the target phrase in the source page body copy (header, nav and footer excluded). Where the count is 0, a sentence needs writing rather than a word wrapping.
Task | Target page (receives the link) | Source page (place the link here) | Existing mentions | Anchor direction | Status
1A | /roof-sprinkler-system/ | /product/rainmaker/ | 6 | roof sprinkler system | Not placed
1A | /roof-sprinkler-system/ | /wildfire-sprinkler-kit/ | 4 | rooftop sprinkler protection | Not placed
1A | /roof-sprinkler-system/ | /fire-embers/ | 3 | roof sprinklers, where ember ignition is discussed | Not placed
1A | /roof-sprinkler-system/ | /blog/what-to-do-in-a-wildfire-evacuation/ | 2 | roof sprinkler system | Not placed
1A | /roof-sprinkler-system/ | /blog/firesmart-your-property-with-wildfire-mitigation/ | 2 | roof sprinkler system | Not placed
1A | /roof-sprinkler-system/ | /blog/does-rain-really-reduce-wildfire-risk/ | 2 | roof sprinklers | Not placed
1B | /mark-3-pump/ | /product/mark-3-b2-10hp-mid-range/ | 13 | Vary across "Mark-3 portable fire pump", "portable fire pumps in Canada", "our Mark-3 pump range" | Not placed
1B | /mark-3-pump/ | /product/mark-3-qs-10hp-high-pressure/ | 11 | Vary across "Mark-3 portable fire pump", "portable fire pumps in Canada", "our Mark-3 pump range" | Not placed
1B | /mark-3-pump/ | /product/rancher-65-gallon/ | 5 | Vary across "Mark-3 portable fire pump", "portable fire pumps in Canada", "our Mark-3 pump range" | Not placed
1B | /mark-3-pump/ | /shop/ | 4 | Vary across "Mark-3 portable fire pump", "portable fire pumps in Canada", "our Mark-3 pump range" | Not placed
1B | /mark-3-pump/ | /product/striker3-13hp-portable/ | 4 | Vary across "Mark-3 portable fire pump", "portable fire pumps in Canada", "our Mark-3 pump range" | Not placed
1B | /mark-3-pump/ | /product/bb-4-21hp-high-pressure-portable/ | 4 | Vary across "Mark-3 portable fire pump", "portable fire pumps in Canada", "our Mark-3 pump range" | Not placed
1B | /mark-3-pump/ | /product/bb-4-18hp-high-pressure-portable/ | 4 | Vary across "Mark-3 portable fire pump", "portable fire pumps in Canada", "our Mark-3 pump range" | Not placed
1B | /mark-3-pump/ | /product/wildfire-bb4-12-16-high-pressure-pump-end-23hp-briggs-stratton-vanguard/ | 3 | Vary across "Mark-3 portable fire pump", "portable fire pumps in Canada", "our Mark-3 pump range" | Not placed
1B | /mark-3-pump/ | /product/striker2-13hp-portable/ | 3 | Vary across "Mark-3 portable fire pump", "portable fire pumps in Canada", "our Mark-3 pump range" | Not placed
1B | /mark-3-pump/ | /product/rancher-no-tank/ | 3 | Vary across "Mark-3 portable fire pump", "portable fire pumps in Canada", "our Mark-3 pump range" | Not placed
1B | /mark-3-pump/ | /product/rancher-125-gallon/ | 3 | Vary across "Mark-3 portable fire pump", "portable fire pumps in Canada", "our Mark-3 pump range" | Not placed
1B | /mark-3-pump/ | /product/mini-striker-2-5hp-portable/ | 3 | Vary across "Mark-3 portable fire pump", "portable fire pumps in Canada", "our Mark-3 pump range" | Not placed
1B | /mark-3-pump/ | /product/b2x-20p-21hp-mid-range-portable/ | 3 | Vary across "Mark-3 portable fire pump", "portable fire pumps in Canada", "our Mark-3 pump range" | Not placed
1B | /mark-3-pump/ | /product/bb-4-23hp-high-pressure-portable/ | 2 | Vary across "Mark-3 portable fire pump", "portable fire pumps in Canada", "our Mark-3 pump range" | Not placed
1C | /fire-embers/ | /roof-sprinkler-system/ | 10 | "fire embers" / "ember ignition" / "how embers start fires" | Not placed
1C | /fire-embers/ | /blog/defensible-space/ | 7 | "fire embers" / "ember ignition" / "how embers start fires" | Not placed
1C | /fire-embers/ | /blog/firesmart-your-property-with-wildfire-mitigation/ | 6 | "fire embers" / "ember ignition" / "how embers start fires" | Not placed
1C | /fire-embers/ | /structure-protection-sprinklers/ | 5 | "fire embers" / "ember ignition" / "how embers start fires" | Not placed
1C | /fire-embers/ | /blog/preparing-for-wildfires-property-owner-guide/ | 5 | "fire embers" / "ember ignition" / "how embers start fires" | Not placed
1C | /fire-embers/ | /blog/preparing-for-wildfire-evacuation/ | 5 | "fire embers" / "ember ignition" / "how embers start fires" | Not placed
1C | /fire-embers/ | /blog/okanagan-wildfire-risks/ | 5 | "fire embers" / "ember ignition" / "how embers start fires" | Not placed
1C | /fire-embers/ | /spiedr-wildfire-sprinkler-kit/ | 4 | "fire embers" / "ember ignition" / "how embers start fires" | Not placed
1C | /fire-embers/ | /blog/wildfire-protection-systems-business-safety/ | 4 | "fire embers" / "ember ignition" / "how embers start fires" | Not placed
1C | /fire-embers/ | /blog/protecting-resort-from-wildfire/ | 4 | "fire embers" / "ember ignition" / "how embers start fires" | Not placed
1D | /spiedr-fire-pump-protection-systems/ | /mark-3-pump/ | 0 | "fire fighting pumps" / "portable water pump for fire fighting" - sentence needs writing | Not placed
1D | /spiedr-fire-pump-protection-systems/ | /waterax-pumps/ | 0 | "fire fighting pumps" / "portable water pump for fire fighting" - sentence needs writing | Not placed
1D | /spiedr-fire-pump-protection-systems/ | /sprinkler-trailers/ | 0 | "fire fighting pumps" / "portable water pump for fire fighting" - sentence needs writing | Not placed
1D | /spiedr-fire-pump-protection-systems/ | /blog/history-of-wildfire-equipment/ | 0 | "fire fighting pumps" / "portable water pump for fire fighting" - sentence needs writing | Not placed
1D | /spiedr-fire-pump-protection-systems/ | /blog/essential-wildland-firefighting-equipment/ | 0 | "fire fighting pumps" / "portable water pump for fire fighting" - sentence needs writing | Not placed
1D | /spiedr-fire-pump-protection-systems/ | /blog/maintenance-tips-for-wildfire-protection-equipment-in-british-columbia-canada/ | 0 | "fire fighting pumps" / "portable water pump for fire fighting" - sentence needs writing | Not placed

## Success Measures
Success Measures
Baseline is 1-30 September 2026. Targets are directional, not commitments - rankings respond to competitor activity and Google algorithm changes outside our control.
Measure | Baseline (Sept 2026) | Target | Review point | Source
Pages with zero in-content inbound links | 48 of 163 | Under 10 | 6 Nov 2026 | Crawl plus link parse
Blog posts with zero in-content inbound links | 45 of 93 | Under 10 | 6 Dec 2026 | Crawl plus link parse
/roof-sprinkler-system/ - best position in its cluster | #12 | Top 10 | 6 Dec 2026 | Semrush Organic Research (ca)
/blog/...bc-fire-bans.../ - best position in its cluster | #25 | Page 2 (top 20) | 6 Dec 2026 | Semrush Organic Research (ca)
GSC clicks (national, monthly) | 488 | Directional improvement | 6 Dec 2026 | Google Search Console
Tracked keywords with volume above 50/mo | 3 of 47 | 20 or more | 6 Oct 2026 | Semrush Position Tracking

## Risks
Risks and Mitigations
Reviewed at each monthly report.
Risk | Likelihood | Impact | Mitigation | Owner
Client approval per page slows Phase 1 past 1 October | Medium | High | Seek batch approval for internal link edits in Week 1 (task 0.6) - these do not change page copy meaningfully | Shawn
The 11-12 September SERP movement continues and masks our gains | Medium | Medium | Baseline captured in Phase 0; report changes against page-level GSC impressions, not position alone | Francis
Theme cannot support hub templates without dev work | Medium | High | Confirmed in Week 1 (task 0.7), before Phase 3 is scheduled | Dev
Internal linking alone does not move page-2 rankings | Medium | Medium | Phase 3 pairs links with a content refresh; if the December review shows no movement, escalate to a content depth and backlink assessment | Francis
The report continues to generate false alarms if 2A slips | Low | High | Owner and hard date assigned; single Semrush change | Francis